## Overall Budget
Example Budget and ongoing costs for implementing a new small business website
Project Costs
Who | Item | Total Cost | Type | Comments
Supplier | Domain name | 58 | Project | Once-off
Internal | Project Lead | 2000 | Project | 0.1 FTE over 4 months
Internal | Subject Matter Experts | 2000 | Project | 0.1 FTE over 4 months | Internal people up to a total of half a day a week
Supplier | Website build | 2500 | Project | Once-off
Supplier | Theme (if custom) | 150 | Project | Once-off
Supplier | Content creation | 1000 | Project | Once-off
Supplier | Applications & Integrations | 500 | Project | Once-off
Supplier | SEO set-up | 1000 | Project | Once-off
Supplier | Training/User Guides | 250 | Project | 1 x half day
Supplier | Website hosting | 220 | Project | $55 x 4 | Starts once website work commences
Supplier | Security Certificate | 400 | Project | $100 x 4 | Starts once website work commences
Total for Project |  | 10078
Ongoing Costs
Supplier | Website Hosting | 55 | Ongoing | Monthly
Supplier | Security Certificate | 100 | Ongoing | Monthly
Supplier | SEO & Marketing | 750 | Ongoing | Monthly
Supplier | Support & Maintenance | 250 | Ongoing | Monthly
Monthly ongoing |  | 1155
Opportunity Cost
Don’t forget you will need access to subject matter experts internally and you'll need someone to lead/coordinate the work too.
Their time costs your business money, which are opportunity costs. So, factor this in too to give you a proper idea of the full cost of delivery.

## Project Budget V Forecast
Example Project Budget & Forecast |  |  |  | With January Actuals
|  | Jan |  | Feb |  | Mar |  | Apr |  | Totals |  | Variance
Details | Capital/Operational | Budget | Actuals/Forecast | Budget | Actuals/Forecast | Budget | Actuals/Forecast | Budget | Actuals/Forecast | Budget | Actuals/Forecast
Domain name | Operational | 58 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 65 | -7
Website hosting | Operational | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 220 | 220 | 0
Security Certificate | Operational | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 400 | 400 | 0
Website build | Capital | 1000 | 1200 | 1500 | 1500 | 0 | 0 | 0 | 0 | 2500 | 2700 | -200
Theme (if custom) | Capital | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0
Content creation | Capital | 0 | 0 | 500 | 500 | 500 | 500 | 0 | 0 | 1000 | 1000 | 0
Applications & Integrations | Capital | 250 | 0 | 250 | 500 | 0 | 0 | 0 | 0 | 500 | 500 | 0
SEO set-up | Capital | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 1000 | 1000 | 0
Training | Capital | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 0
Actual Cost |  | 1613 | 1570 | 2405 | 2655 | 1655 | 1655 | 405 | 405 | 6078 | 6285 | -207
Internal Project Leader | Operational | 500 | 750 | 500 | 500 | 500 | 500 | 500 | 500 | 2000 | 2250 | -250 | Opportunity cost
Internal Subject Matter Experts | Operational | 500 | 350 | 500 | 500 | 500 | 500 | 500 | 500 | 2000 | 1850 | 150 | Opportunity cost
True Cost | [9 empty] | 10078 | 10385 | -307

## Lists
Category | Type of cost
Resources | Project
Materials | Ongoing
Licences
Vendor